## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task Description | Priority | Assigned To | Start Date | End Date | Hours( Task Based Estimated the Testing+Development-Technical Panel) | Story Point( Business Value /Complexity) Estimates how much we can deliver in a sprint+total effort with its tasks with its risk dependencies and other factors(PO + Scrum) | Status
1 | 1 | Registration Form | As a Bank Representive User I need to have form to register myself | Task 1 | To Create a Registration Form using JSP so that user can register himself by entering his details | 1 | Akash | 18-03-2019 |  |  |  | In Progress
|  |  |  | Task 2 | To Create A Controller Class, Service Class,DAO Class, Entity class for Admin, POJO class of customers to Implement MVC | 1 | Rahul and Prabhakar | 18-03-2019 |  |  |  | In Progress
|  |  |  | Task 3 | Setup Spring-Hibernate Configuration files. | 1 | Ankur | 18-03-2019 |  |  |  | In Progress
|  |  |  | Task 4 | On successful registration generate alert Message and redirect to Login Page | 1 | Akash | 18-03-2019 |  |  |  | In Progress
|  | Authentication and Authorization | As a registed user I am able click ‘Login’ link, after keying in‘UserID’ & ‘Password’ field and get his credentials authenticated with the existingdatabase entry. | Task 5 | To create Login Page using JSP so that user can be authenticated | 1 | Sarthak | 18-03-2019 |  |  |  | Not Started
|  |  |  | Task 6 | Authenticate By calling on controller that would authenticate by calling method in DAO via Service Class as per MVC. | 1 | Rahul and Prabhakar | 18-03-2019 |  |  |  | In Progress
|  |  |  | Task 7 | On unsuccessful authentication generate alert Message "Invalid Credentials" | 1 | Sarthak | 18-03-2019 |  |  |  | Not Started
|  |  |  | Task 8 | On successful login redirect to home Page. | 1 | Sarthak | 18-03-2019 |  |  |  | Not Started
|  | Data Base Creation | Creatiing a Database Tables as per BRD | Task 9 | To create Tables as Per BRD using MYSQL for Bank Representative and Customers Details. | 1 | Ankur | 18-03-2019 |  |  |  | In Progress